The 3rd  Narrative Progress Report of TSU  (Pr.5)

Time period 29.06.2014 - 28.03.2015

Prepared by: Kakhaber Bilashvili

- Number of actions has been undertaken during the reported period in accordance with the  Action plan of the project, as follow:

- Working on the preparation of the National tour offers, basing on the template submitted by Pr.6 (GA4 ) – 07.2014;

- Continuation of working on the options of national tours (GA4) – 08. 2014;

- Finalization and submission of  national tours in the proposed format to Pr6 (GA4) – 08.2014 ;

- Preparation of presentation and participation in Project Coordination Group and Network meeting 4 in Constanta, Romania ( GA2) -  09.2014

- In order to prepare the newsletter of the BSTN project, on the request of PR.4, was  prepared and delivered information on the analysis of stakeholder questionnaires distributed in Georgia  (GA3) – 02.2015;

- Preparation works were carried out for arrangement of  PCG5 workshop in Tbilisi – 05. 2015;

- Working on the Cross –border tours in the format suggested, communicating with partners regarding the possible options of tours – 05. 2015